## general_report
Task ID | Task Summary | Parent Task | Σ Remaining Estimate (hours) | Assignee | Status | Resolution | Due Date | Original Estimate | Σ Time Spent | Σ Remaining Estimate | Sub-Tasks
HTOYOTA-1085 | Organize the meeting with Harman Generic Browser responsibles | HTOYOTA-1555 | 3 | Zolotykh Vladimir | Open | Unresolved | 2015-04-04 | 14400 |  | 10800
HTOYOTA-1086 | Get application platform documented / get documentation | HTOYOTA-1514 | 6 | Zolotykh Vladimir | Open | Unresolved | 2015-04-04 | 21600 |  | 21600
HTOYOTA-1143 | TRS/CRS - remove links to Procom | HTOYOTA-1513 | 4 | Zolotykh Vladimir | Open | Unresolved |  | 14400 |  | 14400
HTOYOTA-1281 | Update TRS information for audio formats | HTOYOTA-1513 | 3.5 | Dan Sava | Open | Unresolved | 2015-04-04 | 14400 | 1800 | 12600
HTOYOTA-1288 | HTML5 feature support for Browser | HTOYOTA-1555 | 8 | Zolotykh Vladimir | Open | Unresolved |  | 28800 |  | 28800
HTOYOTA-1289 | Coyote - add test needs to TRS | HTOYOTA-1556 | 20 | Dan Sava | Open | Unresolved |  | 72000 |  | 72000
HTOYOTA-1290 | Estore - add test needs to TRS | HTOYOTA-1557 | 7 | Dan Sava | Open | Unresolved |  | 25200 |  | 25200
HTOYOTA-1371 | Application platform study | HTOYOTA-1514 | 4 | Zolotykh Vladimir | Open | Unresolved |  | 14400 |  | 14400
HTOYOTA-1403 | Set "Affected Department", TBD, Complexity of Internet-Applicaiton TRS in DOORS | HTOYOTA-1513 | 0 | Roman Nikitin | In Progress | Unresolved |  | 21600 | 55800 | 0
HTOYOTA-1471 | Reduce set of used API calls only to those available at system level. | HTOYOTA-1513 | 8 | Zolotykh Vladimir | Open | Unresolved |  | 28800 |  | 28800
HTOYOTA-1473 | Extend HDD with Browser description | HTOYOTA-1515 | 6 | Dan Sava | Open | Unresolved |  | 21600 |  | 21600
HTOYOTA-1474 | analyse Presentation controller document from Browser | HTOYOTA-1555 | 8 | Zolotykh Vladimir | Open | Unresolved |  | 28800 |  | 28800
HTOYOTA-1476 | eStore: Check if all interactions with application platform/other parts of the system are available in the application platform specification | HTOYOTA-1557 | 8 | Dan Sava | Open | Unresolved |  | 28800 |  | 28800
HTOYOTA-1507 | CRS editions, rephrasing and making the statesments clearer and more precise. | HTOYOTA-1513 | 10 | Dan Sava | Open | Unresolved |  | 36000 |  | 36000
HTOYOTA-1508 | Resolving IT related issues ( accounts, rights, access, etc.) | HTOYOTA-1514 | 0.041667 | Zolotykh Vladimir | Open | Unresolved |  | 150 |  | 150
HTOYOTA-1509 | Update TRS for Coyote to include Coyote Screens - Settings | HTOYOTA-1556 | 6 | Dan Sava | Open | Unresolved |  | 21600 |  | 21600
HTOYOTA-1513 | TRS: Revise complexity, revise API calls with focus to CRS |  | 29.5 | Zolotykh Vladimir | Open | Unresolved |  |  | 133200 | 106200 | HTOYOTA-717, HTOYOTA-885, HTOYOTA-1143, HTOYOTA-1281, HTOYOTA-1403, HTOYOTA-1471, HTOYOTA-1507, HTOYOTA-1588
HTOYOTA-1514 | Get Application Platform documented |  | 10.0417 | Zolotykh Vladimir | Open | Unresolved |  |  |  | 36150 | HTOYOTA-1086, HTOYOTA-1371, HTOYOTA-1508
HTOYOTA-1515 | HDD Document: complete deployment sec, process review notes. |  | 26 | Zolotykh Vladimir | Open | Unresolved |  |  |  | 93600 | HTOYOTA-748, HTOYOTA-861, HTOYOTA-1473, HTOYOTA-1586, HTOYOTA-1587
HTOYOTA-1555 | Get Harman pres ctrl of Browser , interface understood. |  | 19 | Zolotykh Vladimir | Open | Unresolved |  |  |  | 68400 | HTOYOTA-1085, HTOYOTA-1288, HTOYOTA-1474
HTOYOTA-1556 | Coyote: update TRS and investigate, document test needs. |  | 26 | Zolotykh Vladimir | Open | Unresolved |  |  |  | 93600 | HTOYOTA-1289, HTOYOTA-1509
HTOYOTA-1557 | eStore: update TRS and investigate , document test needs. |  | 15 | Zolotykh Vladimir | Open | Unresolved |  |  |  | 54000 | HTOYOTA-1290, HTOYOTA-1476
HTOYOTA-1586 | Process HDD review notes by Mr. Lanckman and make necessary corrections in the HDD | HTOYOTA-1515 | 4 | Roman Nikitin | Open | Unresolved |  | 14400 |  | 14400
HTOYOTA-1587 | Conduct the HDD review with Mr. Lanckman | HTOYOTA-1515 | 2 | Zolotykh Vladimir | Open | Unresolved |  | 7200 |  | 7200
HTOYOTA-1588 | Conduct TRS review with Mr. Lanckman | HTOYOTA-1513 | 2 | Zolotykh Vladimir | Open | Unresolved |  | 7200 |  | 7200
HTOYOTA-717 | Add non-functional requirements (TRS) | HTOYOTA-1513 | 0 | Roman Nikitin | Open | Unresolved | 2015-04-04 | 25200 | 75600 | 0
HTOYOTA-748 | Extend / update HDD with Application framework description | HTOYOTA-1515 | 8 | Dan Sava | Open | Unresolved |  | 28800 |  | 28800
HTOYOTA-861 | Finalize Deployment section of the HDD | HTOYOTA-1515 | 6 | Zolotykh Vladimir | Open | Unresolved |  | 21600 |  | 21600
HTOYOTA-885 | Update initial chapters of TRS , DOORS | HTOYOTA-1513 | 2 | Zolotykh Vladimir | Open | Unresolved |  | 7200 |  | 7200
Total |  |  | 251.0833

## Time sheet
Task ID | Summary | Parent task ID | Assignee | 2015-04-20 | 2015-04-21 | 2015-04-22 | 2015-04-23 | 2015-04-24 | 2015-04-25 | 2015-04-26 | 2015-04-27 | 2015-04-28 | 2015-04-29 | 2015-04-30 | 2015-05-01 | 2015-05-02 | 2015-05-03 | 2015-05-04 | 2015-05-05
HTOYOTA-1513 | TRS: Revise complexity, revise API calls with focus to CRS | 0 | Zolotykh Vladimir
HTOYOTA-1514 | Get Application Platform documented | 0 | Zolotykh Vladimir
HTOYOTA-1515 | HDD Document: complete deployment sec, process review notes. | 0 | Zolotykh Vladimir
HTOYOTA-1555 | Get Harman pres ctrl of Browser , interface understood. | 0 | Zolotykh Vladimir
HTOYOTA-1556 | Coyote: update TRS and investigate, document test needs. | 0 | Zolotykh Vladimir
HTOYOTA-1557 | eStore: update TRS and investigate , document test needs. | 0 | Zolotykh Vladimir
HTOYOTA-1143 | TRS/CRS - remove links to Procom | HTOYOTA-1513 | Zolotykh Vladimir
HTOYOTA-1281 | Update TRS information for audio formats | HTOYOTA-1513 | Dan Sava
HTOYOTA-1403 | Set "Affected Department", TBD, Complexity of Internet-Applicaiton TRS in DOORS | HTOYOTA-1513 | Roman Nikitin
HTOYOTA-1471 | Reduce set of used API calls only to those available at system level. | HTOYOTA-1513 | Zolotykh Vladimir
HTOYOTA-1507 | CRS editions, rephrasing and making the statesments clearer and more precise. | HTOYOTA-1513 | Dan Sava
HTOYOTA-1588 | Conduct TRS review with Mr. Lanckman | HTOYOTA-1513 | Zolotykh Vladimir
HTOYOTA-717 | Add non-functional requirements (TRS) | HTOYOTA-1513 | Roman Nikitin
HTOYOTA-885 | Update initial chapters of TRS , DOORS | HTOYOTA-1513
HTOYOTA-1086 | Get application platform documented / get documentation | HTOYOTA-1514 | Zolotykh Vladimir
HTOYOTA-1371 | Application platform study | HTOYOTA-1514 | Zolotykh Vladimir
HTOYOTA-1508 | Resolving IT related issues ( accounts, rights, access, etc.) | HTOYOTA-1514 | Zolotykh Vladimir
HTOYOTA-1473 | Extend HDD with Browser description | HTOYOTA-1515 | Dan Sava
HTOYOTA-1586 | Process HDD review notes by Mr. Lanckman and make necessary corrections in the HDD | HTOYOTA-1515 | Roman Nikitin
HTOYOTA-1587 | Conduct the HDD review with Mr. Lanckman | HTOYOTA-1515 | Zolotykh Vladimir
HTOYOTA-748 | Extend / update HDD with Application framework description | HTOYOTA-1515 | Dan Sava
HTOYOTA-861 | Finalize Deployment section of the HDD | HTOYOTA-1515 | Zolotykh Vladimir
HTOYOTA-1085 | Organize the meeting with Harman Generic Browser responsibles | HTOYOTA-1555 | Zolotykh Vladimir
HTOYOTA-1288 | HTML5 feature support for Browser | HTOYOTA-1555 | Zolotykh Vladimir
HTOYOTA-1474 | analyse Presentation controller document from Browser | HTOYOTA-1555 | Zolotykh Vladimir
HTOYOTA-1289 | Coyote - add test needs to TRS | HTOYOTA-1556 | Dan Sava
HTOYOTA-1509 | Update TRS for Coyote to include Coyote Screens - Settings | HTOYOTA-1556 | Dan Sava
HTOYOTA-1290 | Estore - add test needs to TRS | HTOYOTA-1557 | Dan Sava
HTOYOTA-1476 | eStore: Check if all interactions with application platform/other parts of the system are available in the application platform specification | HTOYOTA-1557 | Dan Sava